## Sheet1
Expenditure List for January, February and March activities 2019
Q1 report
S/No | Date | Description of activity/transaction | Objective | Account | Payee | Amount in SSP | Amount USD
1 | 14/03/2019 | Induction Workshop in Wijrek County | 1.4.1.1 | 1630 | 150 Participants | 60000
2 | 14/03/2019 | Transport To & Fro | 1.4.1.6 | 9779 | Car Hired |  | 200
3 | 27/03/2019 | Training of Traders and Venders in kodok town | 1.3.2.3 | 1630 | 52 Participants | 26260
4 | 27/03/2019 | Training of Cash Distribution Committee (CDC) in wijrek | 1.1.1.1 | 978 | 6 Participants | 3000
5 | 28/03/2019 | Mobilization and senitization of community on VSLA | 1.2.10 | N/A | N/A | N/A | N/A
6 | 29/03/2019 | Training of traders Union and vendors in Lul- Wijrek County | 1.3.2.3 | 1630 | 47 Participants | 23500
7 | 29/03/2019 | Transport To & Fro | 1.1.1.1 | 978 | Car Hired |  | 200
8 | 14/03/2019 | Community mobilization and sensitization on all project activities | 1..4.1.2 | N/A | N/A | N/A | N/A
Next planned activities for the Month of April
1 | 1 | Procurement plan for VSLA, CDMRR, Goats re-stocking, fishing gears, crop seeds and vegetable seeds, tools
2 | 2 | Follow-up of market actors after training
3 | 3 | Identification, selection, registration and verficiation of Cash beneficiaries,
4 | 4 | Identification, selection, registration and verficiation of Fishing gears beneficiaries.
5 | 5 | Follow up with assigned leaders for VSLA beneficiaries identification, selection and verification in wijrek county from the five payam
6 | 6 | Identification, selection, registration and verification of Goats beneficiaries and crops and vegetable seeds and tools in Wijrek county5
7 | 7 | Rapid Market assessment and Price monitoring in all the project sites and market improvement
8 | 8 | Establishment of flood task force community structures for risks reduction
9 | 9 | Training of the established groups for Fishing, VSLA, CMDRR